## LDP Trajectory 2025
Updated 2025 | Allocation | Strategic Site | Tenure | With Consent or Subject to Section 106 | Site Ref | Electoral Division | Address | Completions 2024-25 | Total Capacity | Units Rmng | Cat 1 (U/C) | [11 empty] | Beyond 2036 |  | LDP Supply | Dwellings not started | Check | Anticipated Shortfall | Planning Status | JHLAS History/First Appeared in 5 Year Supply | Strategic Site Build Rates | Cardiff Council Comments 2025 | Description | CHECK | CHECK | CONTACT
[12 empty] | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | Cat 3 | Cat 4
PRIVATE & AFFORDABLE SITES WITH PLANNING PERMISSION OR IN ADOPTED PLAN (includes new s106 sites - i.e. resolved to grant within last 12 months). Strategic Sites Shown First.
Yes | Yes | A | Priv | LDP Allocation | BU107A | Butetown | Land West of Dumballs Road LDP Allocation | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 100 | 200 | 300 | 350 | 350 | 350 | 200 | 150 |  | 0 | 2000 | 2000 | TRUE | 0 | 07/01637 outline signed 16/05/2011. 14/00430 Hybrid = Full: 690 dwellings 15/08/2014 (485 priv, 205HA) Outline: 1,460 dwellings LDP Allocation 21/00783 Out | 2011 | 2022-23 524 2023-24 307 | Vastint app determined on this strategic site (2,500). |  | TRUE | #REF! | Vastint UK Services Limited / Turley
Yes | Yes | A | Affordable | LDP Allocation | BU107B | Butetown | Land West of Dumballs Road LDP Allocation Affordable 20% | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 75 | 100 | 100 | 75 | 50 | 50 | 50 | 0 | 0 | 500 | 500 | TRUE | 0 | 07/01637 outline signed 16/05/2011. 14/00430 Hybrid = Full: 690 dwellings 15/08/2014 (485 priv, 205HA) Outline: 1,460 dwellings LDP Allocation 21/00783 Out | 2011 |  | Vastint app determined on this strategic site (2,500). |  | TRUE | #REF! | Vastint UK Services Limited / Turley
Yes | Yes | B | Priv | LDP Allocation | GR177A | Grangetown | Ferry Road, Gas Works Site | 0 | 400 | 400 | 0 | 0 | 0 | 0 | 50 | 75 | 100 | 75 | 50 | 50 |  |  | 0 | 0 | 400 | 400 | TRUE | 0 | LDP Allocation (500 units) Apportioned 20% AH | 2016 |  | Council has acquired this site. Trajectory provided by housing colleagues. | Updated trajectory. Council has acquired site, forms key site in Housing Programme. Update: The site has obtained demolition consent for demolition of approximately 12 number of industrial buildings/structures (Ref. PRNO/21/00004/MNR). Land remediation is anticipated to commence in 2022 with construction in 2023. | TRUE | #REF! | Cardiff Council Housing
Yes | Yes | B | Affordable | LDP Allocation | GR177B | Grangetown | Ferry Road, Gas Works Site | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 |  |  |  |  | 0 | 0 | 100 | 100 | TRUE | 0 | LDP Allocation (500 units) Apportioned 20% AH | 2016 |  | Council has acquired this site. Trajectory provided by housing colleagues. | Updated trajectory. Council has acquired site, forms key site in Housing Programme. Update: The site has obtained demolition consent for demolition of approximately 12 number of industrial buildings/structures (Ref. PRNO/21/00004/MNR). Land remediation is anticipated to commence in 2022 with construction in 2023. | TRUE | #REF! | Cardiff Council Housing
Yes | Yes | C | Priv | With Planning Permission | FA107 | Fairwater | Part 1 of Phase 2A, South of Llantrisant Road Redrow Homes "Cwrt Sant Ioan" / Danescourt Part 1 | 1 | 71 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 18/01184 RM 19/12/2018 | 2021 |  | Complete 2025 |  | TRUE | #REF! | -
Yes | Yes | C | Priv | With Planning Permission | SF43A | Pentyrch & St Fagans | Parcel P2 Of Phase 2, Land North Of Pentrebane Rd (Pendown P2) | 0 | 90 | 90 | 0 | 2026: 60; 2027: 30; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 90 | 90 | TRUE | 0 | 22/00133 RM 01/11/2023 | New site 2024 |  |  | APPLICATION FOR THE APPROVAL OF RESERVED MATTERS (APPEARANCE, SCALE, LAYOUT, LANDSCAPING AND NON-STRATEGIC ACCESS) FOR THE DEVELOPMENT OF 139 DWELLINGS FORMING PARCEL P2 OF PHASE 2 PURSUANT TO OUTLINE PLANNING PERMISSION 14/02733/MJR | TRUE | #REF! | Lichfields / Redrow
Yes | Yes | C | Affordable | With Planning Permission | SF43B | Pentyrch & St Fagans | Parcel P2 Of Phase 2, Land North Of Pentrebane Rd (Pendown P2) Affordable | 0 | 38 | 38 | 0 | 2026: 15; 2027: 15; 2028: 8; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 38 | 38 | TRUE | 0 | 22/00133 RM 01/11/2023 | New site 2024 |  |  | APPLICATION FOR THE APPROVAL OF RESERVED MATTERS (APPEARANCE, SCALE, LAYOUT, LANDSCAPING AND NON-STRATEGIC ACCESS) FOR THE DEVELOPMENT OF 139 DWELLINGS FORMING PARCEL P2 OF PHASE 2 PURSUANT TO OUTLINE PLANNING PERMISSION 14/02733/MJR | TRUE | #REF! | Lichfields / Redrow
Yes | Yes | C | Priv | With Planning Permission | CR29A | Pentyrch & St Fagans | Plasdwr residue, North West Cardiff Outline Creigiau St Fagans Electoral Division | 0 | 2575 | 2575 | 0 | 0 | 150 | 150 | 200 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 0 | 0 | 2250 | 2250 | FALSE | 325 | 14/02733 Outline Granted 20/03/2017 Up to 5,970 residential units. Cregiau & St Fagans wards. | 2017 | 2017-18 39 2018-19 128 2019-21 270 2021-22 174 2022-23 114 2023-24 92 | Overall Plasdwr figure for the Outline consent has been revised downwards due to lower than anticipated capacity following discussion with Litchfields. Outline residue also takes account of new consents granted during 24/25 | Plasdwr Residue | FALSE | #REF! | Lichfields / Redrow
Yes | Yes | C | Affordable | With Planning Permission | CR29ii | Pentyrch & St Fagans | Plasdwr residue, North West Cardiff (Affordable) Outline Creigiau St Fagans Electoral Division | 0 | 1107 | 1107 | 0 | 0 | 0 | 0 | 57 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 0 | 0 | 1107 | 1107 | TRUE | 0 | 14/02733 Outline Granted 20/03/2017 Up to 5,970 residential units. Cregiau & St Fagans wards 30% Affordable. | 2017 | 2019-21 89 2021-22 39 2022-23 92 2023-24 7 | Overall Plasdwr figure for the Outline consent has been revised downwards due to lower than anticipated capacity following discussion with Litchfields. Outline residue also takes account of new consents granted during 24/25 | Plasdwr Residue | TRUE | #REF! | Lichfields / Redrow
Yes | Yes | C | Priv | With Planning Permission | RA71 | Radyr & Morganstown | Plasdwr residue, North West Cardiff Outline Radyr Electoral Division (land west of 2b, Phase 1) | 0 | 128 | 128 | 0 | 0 | 0 | 0 | 12 | 58 | 58 | [5 empty] | 0 | 0 | 128 | 128 | TRUE | 0 | 14/02733 Outline Granted 20/03/2017 Up to 5,970 residential units. Radyr ward 70% Private | 2017 |  | Overall Plasdwr figure for the Outline consent has been revised downwards due to lower than anticipated capacity following discussion with Litchfields. Outline residue also takes account of new consents granted during 24/25 | Plasdwr Residue | TRUE | #REF! | Lichfields / Redrow
Yes | Yes | C | HA | With Planning Permission | RA71ii | Radyr & Morganstown | Plasdwr residue, North West Cardiff (Affordable) Outline Radyr Electoral Division (land west of 2b, Phase 1) | 0 | 55 | 55 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 27; 2030: 28; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 55 | 55 | TRUE | 0 | 14/02733 Outline Granted 20/03/2017 Up to 5,970 residential units. Radyr ward 30% Affordable. | 2017 |  | Plasdwr residue as at 1st April 24. i.e. 5,970 minus RM apps consented as at 31st March 2024 [166 units, 335 units and 128 units] = 5,341 units remaining, split across wards and split to reflect market / affordable target | Plasdwr Residue | TRUE | #REF! | Lichfields / Redrow
Yes | Yes | C | Priv | With Planning Permission | RA72F | Radyr & Morganstown | Parcel 2b of Phase 1, Land West of Clos Parc Radyr and north of Llantrisant Road (Redrow) | 16 | 116 | 64 | 63 | 2026: 1; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 64 | 1 | TRUE | 0 | 19/03279/MJR RM 18/02/2022 | 2022 |  | Under construction | Phase 1 of Redrow's consent for 5,970 dwellings. APPLICATION FOR THE APPROVAL OF RESERVED MATTERS FOR THE DEVELOPMENT OF 167 DWELLINGS, PURSUANT TO OUTLINE PLANNING PERMISSION 14/02733/MJR | TRUE | #REF! | Lichfields / Redrow
Yes | Yes | C | Affordable | With Planning Permission | RA72Fii | Radyr & Morganstown | Parcel 2b of Phase 1, Land West of Clos Parc Radyr and north of Llantrisant Road (Redrow) Affordable | 22 | 50 | 28 | 28 | 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 28 | 0 | TRUE | 0 | 19/03279/MJR RM 18/02/2022 | 2022 |  | Wider site Under construction | Phase 1 of Redrow's consent for 5,970 dwellings. APPLICATION FOR THE APPROVAL OF RESERVED MATTERS FOR THE DEVELOPMENT OF 167 DWELLINGS, PURSUANT TO OUTLINE PLANNING PERMISSION 14/02733/MJR | TRUE | #REF! | Lichfields / Redrow
Yes | Yes | C | Priv | With Planning Permission | SF42D | Pentyrch & St Fagans | Part 2 of Phase 2A, Land North and South of Llantrisant Road "Cwrt St Ioan" Danescourt part 3) | 32 | 84 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 19/03248 RM 22/07/2021 | 2022 |  | Complete 2025 |  | TRUE | #REF! | -
Yes | Yes | C | Priv | With Planning Permission | RA72C | Radyr & Morganstown | Phase 1B, Land North of Llantrisant Road Bellway Homes Limited "Rhiwlas" | 9 | 102 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 18/01318 RM 18/12/2019 | 2021 |  | Complete 2025 |  | TRUE | #REF! | -
Yes | Yes | C | Affordable | With Planning Permission | RA72Cii | Radyr & Morganstown | Phase 1B, Land North of Llantrisant Road Bellway Homes Limited (Affordable) | 5 | 18 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 18/01318 RM 18/12/2019 | 2021 |  | Complete 2025 |  | TRUE | #REF! | -
Yes | Yes | C | Priv | With Planning Permission | RA72G | Radyr & Morganstown | Land North of Clos Parc Radyr | 0 | 34 | 34 | 0 | 2026: 17; 2027: 17; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 34 | 34 | TRUE | 0 | 21/02465 Full 09/02/2023 | 2023 |  |  | 48 dwellings | TRUE | #REF! | Redrow
Yes | Yes | C | Affordable | With Planning Permission | RA72Gii | Radyr & Morganstown | Land North of Clos Parc Radyr (Affordable) | 0 | 14 | 14 | 0 | 2026: 10; 2027: 4; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 14 | 14 | TRUE | 0 | 21/02465 Full 09/02/2023 | 2023 |  |  | 48 dwellings | TRUE | #REF! | Redrow
Yes | Yes | C | Private | With Planning Permission | RA72H | Radyr & Morganstown | Parcel 2A of Phase 1 | 0 | 196 | 187 | 9 | 2026: 25; 2027: 25; 2028: 50; 2029: 50; 2030: 28 | 187 | 196 | TRUE | 0 | 24/00406 RM 15/10/2024 | 2025 |  | Under construction | Application for the approval of reserved matters (appearance, scale, layout, landscaping and non-strategic access) pursuant to outline planning permission 14/02733/MJR for the development of 280 dwellings, forming Parcel 2A of Phase 1. | TRUE | #REF!
Yes | Yes | C | Affordable | With Planning Permission | RA72Hi | Radyr & Morganstown | Parcel 2A of Phase 1 | 0 | 84 | 84 |  | 2026: 40; 2027: 44 | 84 | 84 | TRUE | 0 | 24/00406 RM 15/10/2024 | 2025 |  |  | Application for the approval of reserved matters (appearance, scale, layout, landscaping and non-strategic access) pursuant to outline planning permission 14/02733/MJR for the development of 280 dwellings, forming Parcel 2A of Phase 1. | TRUE | #REF!
Yes | Yes | C | Private | With Planning Permission | SF44A | Pentyrch & St Fagans | Parcel 2E/F of Phase 1, Land off Pentrebane Drive (Gwel y Garth) | 0 | 236 | 236 |  | 2027: 50; 2028: 50; 2029: 50; 2030: 50; 2031: 36 | 236 | 236 | TRUE | 0 | 21/00826 RM 12/04/2024 | 2025 |  |  | APPLICATION FOR THE APPROVAL OF RESERVED MATTERS (APPEARANCE, SCALE, LAYOUT, LANDSCAPING AND ACCESS) FOR RESIDENTIAL DEVELOPMENT, FORMING PARCEL 2E/F OF PHASE 1 (LAND OFF PENTREBANE DRIVE AND NORTH OF ST FAGANS RD), PURSUANT TO OUTLINE PLANNING PERMISSION 14/02733/MJR.
Yes | Yes | C | Affordable | With Planning Permission | SF44B | Pentyrch & St Fagans | Parcel 2E/F of Phase 1, Land off Pentrebane Drive (Gwel y Garth) | 0 | 99 | 99 |  | 2026: 50; 2027: 49 | 99 | 99 | TRUE |  | 21/00826 RM 12/04/2024 | 2025 |  |  | APPLICATION FOR THE APPROVAL OF RESERVED MATTERS (APPEARANCE, SCALE, LAYOUT, LANDSCAPING AND ACCESS) FOR RESIDENTIAL DEVELOPMENT, FORMING PARCEL 2E/F OF PHASE 1 (LAND OFF PENTREBANE DRIVE AND NORTH OF ST FAGANS RD), PURSUANT TO OUTLINE PLANNING PERMISSION 14/02733/MJR.
Yes | Yes | C | Private | With Planning Permission | SF45A | Pentyrch & St Fagans | Land South of Llantrisant Road, Parcel 2D within Phase 1 | 0 | 148 | 148 |  | 2026: 50; 2027: 50; 2028: 48 | 148 | 148 | TRUE | 0 | 23/02365/ RM 28/05/2024 | 2025 |  |  | Application for approval of Reserved Matters pursuant to permission 14/02733/MJR for 211 dwellings at Parcel 2D of Phase 1, Land South of Llantrisant Road, North West Cardiff
Yes | Yes | C | Affordable | With Planning Permission | SF45B | Pentyrch & St Fagans | Land South of Llantrisant Road, Parcel 2D within Phase 1 | 0 | 63 | 63 |  | 2026: 30; 2027: 33 | 63 | 63 | TRUE | 0 | 23/02365/ RM 28/05/2025 | 2025 |  |  | Application for approval of Reserved Matters pursuant to permission 14/02733/MJR for 211 dwellings at Parcel 2D of Phase 1, Land South of Llantrisant Road, North West Cardiff
Yes | Yes | D | Priv | LDP Allocation | CR30 | Pentyrch & St Fagans | Junction 33 LDP allocation residue | 0 | 350 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 60 | 100 | 100 | 60 | 0 | 0 | 350 | 350 | TRUE | 0 | LDP allocation to 2026 (2,000 total) | 2016 | 2019-21 90 2021-22 70 2022-23 95 2023-24 57 | Residue of LDP allocation (i.e. 2,000 - 1,500) Market units |  | TRUE | #REF! | Persimmon Homes East Wales
Yes | Yes | D | Affordable | LDP Allocation | CR30 | Pentyrch & St Fagans | Junction 33 LDP allocation residue | 0 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 30 | 35 | 35 | 30 | 0 | 0 | 150 | 150 | TRUE | 0 | LDP allocation to 2026 (2,000 total) | 2016 | 2019-21 27 2021-22 21 2022-23 6 2023-24 21 | Residue of LDP allocation (i.e. 2,000 - 1,500) Affordable target |  | TRUE | #REF! | Persimmon Homes East Wales
Yes | Yes | D | Priv | With Planning Permission | CR30A | Pentyrch & St Fagans | North of Junction 33 (Strategic Site D) Outline residue (Private) | 0 | 596 | 596 | 0 | 0 | 0 | 60 | 90 | 90 | 90 | 90 | 90 | 86 |  |  | 0 | 0 | 596 | 596 | TRUE | 0 | LDP Allocation (2,000 units) 14/00852 Outline application 1,500 units resolved to grant subject to s106 on 08/02/2017. Signed 07/09/2017 | 2016 |  | Residue of outline consent (i.e. 1,500 minus phases 1,2 &3) Market units | Developer to advise | TRUE | #REF! | Persimmon Homes East Wales
Yes | Yes | D | Affordable | With Planning Permission | CR30Aii | Pentyrch & St Fagans | North of Junction 33 (Strategic Site D) Outline residue (30% AH LDP Target) | 0 | 111 | 111 | 0 | 2026: 0; 2027: 0; 2028: 50; 2029: 50; 2030: 11; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 111 | 111 | TRUE | 0 | LDP Allocation (2,000 units) 14/00852 Outline application 1,500 units resolved to grant subject to s106 on 08/02/2017. Signed 07/09/2017 | 2016 |  | Residue of outline consent (i.e. 1,500 minus phases 1,2 &3) Affordable target | Developer to advise | TRUE | #REF! | Persimmon Homes East Wales
Yes | Yes | D | Priv | With Planning Permission | CR30B | Pentyrch & St Fagans | Phase 1 & 2 North of Junction 33 "The Parish" (Persimmon) & "Regency Park" (Charles Church) | 0 | 317 | 40 | 0 | 2026: 0; 2027: 40; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 40 | 40 | TRUE | 0 | 18/00696 RM 01/08/2019 | 2021 |  | Under construction | RESERVED MATTERS OF OUTLINE PLANNING PERMISSION (14/00852/DCO) FOR A RESIDENTIAL DEVELOPMENT OF 374 DWELLINGS | TRUE | #REF! | -
Yes | Yes | D | Priv | With Planning Permission | CR30C | Pentyrch & St Fagans | Phase 3 North of Junction 33 "The Parish" (Persimmon) | 59 | 143 | 42 | 42 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 42 | 0 | TRUE | 0 | 21/00808 RM 16/03/2022 | 2022 |  | Under construction | NEW SITE: APPROVAL IS SOUGHT FOR THE RESERVED MATTERS OF THE OUTLINE PLANNING PERMISSION (14/00852/DCO) FOR A RESIDENTIAL DEVELOPMENT OF 173 DWELLINGS | TRUE | #REF! | -
Yes | Yes | D | Affordable | With Planning Permission | CR30Cii | Pentyrch & St Fagans | Phase 3 North of Junction 33 "The Parish" (Persimmon) Affordable | 0 | 26 | 8 | 8 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 8 | 0 | TRUE | 0 | 21/00808 RM 16/03/2022 | 2022 |  | Under construction | NEW SITE: APPROVAL IS SOUGHT FOR THE RESERVED MATTERS OF THE OUTLINE PLANNING PERMISSION (14/00852/DCO) FOR A RESIDENTIAL DEVELOPMENT OF 173 DWELLINGS | TRUE | #REF! | -
Yes | Yes | D | Private | With Planning Permission | CR30D | Pentyrch & St Fagans | Phase 4a Land North of J33 | 0 | 74 | 74 | 6 | 2026: 50; 2027: 18 | 74 | 68 | TRUE | 0 | 23/02401 RM | 2025 |  | Under construction | Approval of access, appearance, landscaping, layout and scale for outline reference. Phase 4A, ("the reserved matters") pursuant to planning permission 14/00852/DCO as prescribed by conditions 1 (the Reserved Matters), 4 (Access), 7 (Rapid Transit Route), 8 (Car Parking), 9 (Cycle Parking), 11 (Safeguarding of Changing Facilities), 12 (Adoptable Areas), 13 (Refuse), 14 (Levels), 15 (Landscaping), 16 (Biodiversity Through Design), 21 (Car Charging), 31 (Western LEAP), 33 (Trees), 44 (Road Traffic Noise), 48 (Foul Drainage) & 49 (Surface Water Drainage)
Yes | Yes | E | Priv | LDP Allocation | CR31A | Pentyrch & St Fagans | South of Creigiau (Strategic Site E) | 0 | 455 | 455 | 0 | 0 | 10 | 60 | 70 | 80 | 90 | 80 | 65 |  |  |  | 0 | 0 | 455 | 455 | TRUE | 0 | LDP Allocation (650 units) Outline application received 19/02523/MJR | 2016 |  | Trajectory in keeping with that provided by agent LDP | Outline application submitted. Developer to advise | TRUE | #REF! | -
Yes | Yes | E | Affordable | LDP Allocation | CR31B | Pentyrch & St Fagans | South of Creigiau (Strategic Site E) (30% AH LDP Target) | 0 | 195 | 195 | 0 | 0 | 20 | 30 | 40 | 40 | 30 | 25 | 10 | 0 |  |  | 0 | 0 | 195 | 195 | TRUE | 0 | LDP Allocation (650 units) Outline application received 19/02523/MJR | 2016 |  | Trajectory in keeping with that provided by agent LDP | Outline application submitted. Developer to advise | TRUE | #REF! | -
Yes | Yes | F | Priv | With Planning Permission | LV134 (A) | Lisvane & Thornhill | Churchlands Residue (Private) Outline for 1,000 units (Residue at 1st April) | 0 | 131 | 131 | 0 | 2026: 0; 2027: 30; 2028: 45; 2029: 45; 2030: 11; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 131 | 131 | TRUE | 0 | 13/02000 1,200 units allowed on appeal 14/02891 Outline 22/12/2017 (1,000 units) Applications currently being determined: Phases 1D, 2D & 1Ci. These will appear in schedule once consented | 2016 |  | Outline application residue. | Chruchlands residue | TRUE | #REF! | Redrow
Yes | Yes | F | Affordable | With Planning Permission | LV134 (B) | Lisvane & Thornhill | Churchlands Residue (Affordable) Outline for 1,000 units (Residue at 1st April) | 0 | 56 | 56 | 0 | 2026: 0; 2027: 0; 2028: 12; 2029: 24; 2030: 20; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 56 | 56 | TRUE | 0 | 13/02000 1,200 units allowed on appeal 14/02891 Outline 22/12/2017 (1,000 units) Applications currently being determined: Phases 1D, 2D & 1Ci. These will appear in schedule once consented | 2016 |  | Outline application residue (affordable estimate) | Chruchlands residue | TRUE | #REF! | Redrow
Yes | Yes | F | Priv | With Planning Permission | LV134G | Lisvane & Thornhill | Phase 2C, Churchlands | 13 | 51 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 19/03230 RM 01/09/2021 | 2023 |  | Complete 2025 |  | TRUE | #REF! | Redrow
Yes | Yes | F | Affordable | With Planning Permission | LV134Gii | Lisvane & Thornhill | Phase 2C, Churchlands | 15 | 15 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 19/03230 RM 01/09/2021 | 2023 |  | Complete 2025 |  | TRUE | #REF! | Redrow
Yes | Yes | F | Priv | With Planning Permission | LV134H | Lisvane & Thornhill | Phase 1C(II) Churchlands/ Maerdy Lane "Plas Ty Draw, Phase 3" | 34 | 78 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 19/02750 RM 10/08/2021 | 2023 |  | Complete 2025 |  | TRUE | #REF! | Redrow
Yes | Yes | F | Priv | With Planning Permission | LV134I | Lisvane & Thornhill | Phase 2D Churchlands North & East of Lisvane | 0 | 73 | 73 | 28 | 2026: 45; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 73 | 45 | TRUE | 0 | 19/03247 RM 17/08/2022 | 2023 |  | Under construction | RM for Phase 2d 96 units | TRUE | #REF! | Redrow
Yes | Yes | F | Affordable | With Planning Permission | LV134ii | Lisvane & Thornhill | Phase 2D Churchlands North & East of Lisvane (Affordable) | 0 | 23 | 23 | 0 | 2026: 23; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 23 | 23 | TRUE | 0 | 19/03247 RM 17/08/2022 | 2023 |  |  | RM for Phase 2d 96 units | TRUE | #REF! | Redrow
Yes | Yes | F | Priv | With Planning Permission | LV134J | Lisvane & Thornhill | Phase 1D, Churchlands, Land North and East of Lisvane | 7 | 22 | 15 | 15 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 15 | 0 | TRUE | 0 | 19/03241 RM 10/03/2023 | 2023 |  | Under construction. | RM for Phase 1d 47 units | TRUE | #REF! | Redrow
Yes | Yes | F | Affordable | With Planning Permission | LV134J | Lisvane & Thornhill | Phase 1D, Churchlands, Land North and East of Lisvane | 26 | 26 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 19/03241 RM 10/03/2023 | 2023 |  | Complete 2025 | RM for Phase 1d 47 units | TRUE | #REF! | Redrow
Yes | Yes | F | Priv | LDP Allocation | LV138A SM74A | Lisvane & Thornhill | Strategic Site F - North East Cardiff - West of Pontprennau Residue (Private) | 0 | 624 | 624 | 0 | 0 | 0 | 0 | 0 | 75 | 100 | 100 | 125 | 125 | 99 |  | 0 | 0 | 624 | 624 | TRUE | 0 | LDP Allocation Residue (4,500 units) minus Churchlands 1,000 units, Land off Cefn Mably Rd (51 units), 45 units Ty Draw, 13 units Moor Lynch, 2,500 units NE Cardiff 70% Private | 2016 |  | LDP allocation residue (taking account of Churchlands, Cefn Mably Rd and N of Ty Draw Rd). Split across 2 Wards | LDP allocation residue | TRUE | #REF! | NE Cardiff Consortium
Yes | Yes | F | Affordable | LDP Allocation | LV138B SM74B | Lisvane & Thornhill | Strategic Site F - North East Cardiff - West of Pontprennau Residue (Affordable - indicative based on 30% target). | 0 | 267 | 267 | 0 | 0 | 0 | 0 | 0 | 25 | 40 | 50 | 50 | 50 | 40 | 12 | 0 | 0 | 267 | 267 | TRUE | 0 | LDP Allocation Residue (4,500 units) minus Churchlands 1,000 units, Land off Cefn Mably Rd (51 units), 45 units Ty Draw, 13 units Moor Lynch, 2,500 units NE Cardiff 30% Affordable | 2016 |  | LDP allocation residue (affordable estimate) taking account of Churchlands, Cefn Mably Rd and N of Ty Draw Rd). Split across 2 Wards | LDP allocation residue | TRUE | #REF! | NE Cardiff Consortium
Yes | Yes | F | Priv | LDP Allocation | LV150 / NP60 | Pontprennau/ Old St. M | North East Cardiff, Land south of the M4 to the east of Lisvane, West of Pontprennau (Taylor Wimpey) | 0 | 2050 | 2050 | 0 | 0 | 100 | 150 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 0 | 0 | 1850 | 1850 | FALSE | 200 | 19/02330 Outline Committee resolved to grant subject to s106 | 2023 | 2014-15 49 2019-21 71 2021-22 67 2022-23 106 2023-24 101 | S106 signed July 2024 | Mixed use development up to 2,500 new homes to include affordable housing | FALSE | #REF! | Taylor Wimpey
Yes | Yes | F | Affordable | LDP Allocation | LV150ii / NP60ii | Pontprennau/ Old St. M | North East Cardiff, Land south of the M4 to the east of Lisvane, West of Pontprennau 30% Affordable | 0 | 450 | 450 | 0 | 0 | 0 | 25 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 425 | 425 | FALSE | 25 | 19/02330 Outline Committee resolved to grant subject to s106 | 2023 | 2019-21 6 2021-22 18 2022-23 22 2023-24 42 | S106 signed July 2024 | Mixed use development up to 2,500 new homes to include affordable housing | FALSE | #REF! | Taylor Wimpey
Yes | Yes | F | Priv | With Planning Permission | LV134C | Lisvane | Churchlands 2A, Redrow Homes | 3 | 11 | 2 | 0 | 2026: 2; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 2 | 2 | TRUE | 0 | 19/01973 RM 04/11/2019 | 2021 |  | Under construction |  | TRUE | #REF! | -
Yes | Yes | F | Priv | With Planning Permission | LV134D | Lisvane | Churchlands 2B, Redrow Homes | 9 | 56 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 19/02677 RM 28/08/2020 | 2021 |  | Complete 2025 |  | TRUE | #REF! | -
Yes | Yes | F | Priv | With Planning Permission | LV134E | Lisvane | Churchlands, Phase 3, Bellway "Longwood Grange" | 28 | 216 | 146 | 30 | 2026: 100; 2027: 16; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 146 | 116 | TRUE | 0 | 19/01113 RM 19/12/2019 | 2021 |  | Under construction |  | TRUE | #REF! | -
Yes | Yes | F | Priv | With Planning Permission | LV134Eii | Lisvane | Churchlands, Phase 3, Bellway "Longwood Grange" (Affordable) | 3 | 54 | 9 | 0 | 2026: 9; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 9 | 9 | TRUE | 0 | 19/01113 RM 19/12/2019 | 2021 |  | Under construction |  | TRUE | #REF! | -
Yes | Yes | F | Affordable | With Planning Permission | NP200 | Pontprennau/ Old St. M | Land north of Ty Draw Road (United Welsh in association with Edenstone Homes) | 45 | 45 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 19/02648 RM Committee 02/02/2022 resolved to grant subject to s106 | 2022 |  | Complete 2025 | DEVELOPMENT OF 45 AFFORDABLE HOUSING UNITS | TRUE | #REF! | RPS / United Welsh in association with Edenstone Homes
Yes | Yes | F | Private | With Planning Permission | LV134K | Lisvane & Thornhill | Land at Church Farm | 0 | 144 | 144 |  | 2026: 50; 2027: 50; 2028: 44 | 144 | 144 | TRUE | 0 | 23/00965 Hybrid Application - Outline for 144 dwellings, Full for 43 Private 18 affordable | 2025 |  |  | Hybrid planning application for the residential development of up to 205 dwellings including associated drainage attenuation, open space and highways infrastructure comprising a full application for 61 dwellings (Phase 1) and an outline application for up to 144 dwellings with all matters reserved apart from access (Phase 2).
Yes | Yes | F | Private | With Planning Permission | LV134Ki | Lisvane & Thornhill | Land at Church Farm | 0 | 43 | 43 |  | 2026: 20; 2027: 23 | 43 | 43 | TRUE | 0 | 23/00965 Hybrid Application - Outline for 144 dwellings, Full for 43 Private 18 affordable | 2025 |  |  | Hybrid planning application for the residential development of up to 205 dwellings including associated drainage attenuation, open space and highways infrastructure comprising a full application for 61 dwellings (Phase 1) and an outline application for up to 144 dwellings with all matters reserved apart from access (Phase 2).
Yes | Yes | F | Affordable | With Planning Permission | LV134L | Lisvane & Thornhill | Land at Church Farm | 0 | 18 | 18 |  | 2026: 10; 2027: 8 | 18 | 18 | TRUE | 0 | 23/00965 Hybrid Application - Outline for 144 dwellings, Full for 43 Private 18 affordable | 2025 |  |  | Hybrid planning application for the residential development of up to 205 dwellings including associated drainage attenuation, open space and highways infrastructure comprising a full application for 61 dwellings (Phase 1) and an outline application for up to 144 dwellings with all matters reserved apart from access (Phase 2).
Yes | Yes | G | Priv | With Planning Permission | SM64G | Pontprennau/ Old St. M | Land East of Church Road and North and South of Bridge Road PHASE 6 | 9 | 182 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 19/03205 RM 22/10/2020 | 2021 |  | Complete 2025 |  | TRUE | #REF! | -
Yes | Yes | G | Priv | LDP Allocation | SM75A | Pontprennau/ Old St. M | Land adjacent to St Julian's House, Bridge Road "Sant Silian" Dandara West Limited | 35 | 99 | 43 | 43 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 43 | 0 | TRUE | 0 | 20/02078 Outline 31/08/2021 22/00665 RM 143 units Pending | 2022 |  | Under construction | RESIDENTIAL DEVELOPMENT OF UP TO 160 UNITS | TRUE | #REF! | Pip Cole / PMG Development Ltd
Yes | Yes | G | Affordable | LDP Allocation | SM75B | Pontprennau/ Old St. M | Land adjacent to St Julian's House, Bridge Road "Sant Silian" Dandara West Limited Affordable | 31 | 44 | 13 | 13 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 13 | 0 | TRUE | 0 | 20/02078 Outline 31/08/2021 22/00665 RM 143 units Pending | 2022 |  | Under construction | RESIDENTIAL DEVELOPMENT OF UP TO 160 UNITS | TRUE | #REF! | Pip Cole / PMG Development Ltd
Yes | Yes | G | Priv | LDP Allocation | SM65K | Pontprennau/ Old St. M | Land at St Julians Manor, Bridge Road | 7 | 7 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 21/01301 Full 20/03/2023 | New site 2024 |  | Complete 2025 | Within Strategic Site G | TRUE | #REF!
Yes | Yes | G | Priv | LDP Allocation | SM65M | Pontprennau/ Old St. M | Land at St Julians House, Bridge Road | 0 | 2 | 2 | 0 | 2026: 2; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 2 | 2 | TRUE | 0 | 22/01466 Full 28/07/2023 | New site 2024 |  |  | Within Strategic Site G | TRUE | #REF!
Yes | Yes | G | Priv | LDP Allocation | SM65N | Pontprennau/ Old St. M | Land at The Granary, Bridge Road | 0 | 2 | 2 | 0 | 2026: 2; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 2 | 2 | TRUE | 0 | 21/01173 Full 14/09/2023 | New site 2024 |  |  | Within Strategic Site G | TRUE | #REF!
Yes | Yes |  | Priv | LDP Allocation | H1.1 | Trowbridge | H1.1 Land at Areas 9-12, St Mellons | 0 | 105 | 105 | 0 | 2026: 0; 2027: 0; 2028: 50; 2029: 55; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 105 | 105 | TRUE | 0 | New Site: Non Strategic LDP Allocation. Forecast based on agreed LDP Trajectories. | 2016 |  | No change proposed. Cardiff Housing site |  | TRUE | #REF! | Cardiff Council
Yes | Yes |  | Affordable | LDP Allocation | H1.1 | Trowbridge | H1.1 Land at Areas 9-12, St Mellons | 0 | 45 | 45 | 0 | 2026: 0; 2027: 0; 2028: 22; 2029: 23; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 45 | 45 | TRUE | 0 | New Site: Non Strategic LDP Allocation. Forecast based on agreed LDP Trajectories. | 2016 |  | No change proposed. Cardiff Housing site |  | TRUE | #REF! | Cardiff Council
Yes | Yes |  | Priv | LDP Allocation | H1.3 | Llandaff | H1.3 Rookwood Hospital | 0 | 90 | 90 | 0 | 2026: 10; 2027: 40; 2028: 40; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 90 | 90 | TRUE | 0 | New Site: Non Strategic LDP Allocation. Forecast based on agreed LDP Trajectories. | 2016 |  | Updated trajectory based on information from health board |  | TRUE | #REF! | Cardiff Vale UHB
Yes | Yes |  | Affordable | LDP Allocation | H1.4 | Canton | H1.4 Former Lansdowne Hospital (Lovells) | 0 | 106 | 106 | 0 | 2026: 60; 2027: 46; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 106 | 106 | TRUE | 0 | Non Strategic LDP Allocation. Forecast based on agreed LDP Trajectories. 21/02054 Full s.106 31st March 2022 | 2016 |  | Under construction | Updated trajectory. 106 homes (44 houses 62 apartments in 3 blocks). Site is being pursued as 100% affordable. The council has a land interest in the development | TRUE | #REF! | Cardiff Council Housing
Yes | Yes |  | Affordable | LDP Allocation | RU105 | Rumney | H1.6 Land at former St John's College/Land at Greenway Road | 0 | 58 | 58 | 0 | 2026: 30; 2027: 28; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 58 | 58 | TRUE | 0 | 14/00504 Full s106 21/02945 Full Revised signed July 2024 | 2016 |  | LDP allocation / with consent. Anticipated within 5 years. |  | TRUE | #REF! | Cardiff Community Housing Association (CCHA) / Asbri Planning
Sites 10+ with Planning Permission
Yes |  |  | Priv | With Planning Permission | AD242 | Adamsdown | Riva Bingo, Agate Street | 39 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | 0 | 15/02271 Outline Committee 12/04/2017 resolved to grant subject to s106 17/02338 RM granted 14/03/2018 21/01595 Full 21/01595 | 2017 |  | Complete 2025 |  | TRUE | #REF! | -
Yes |  |  | Priv | With Planning Permission | AD259 | Adamsdown | 4-6 Broadway | 0 | 12 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | TRUE | 0 | 18/01995 Full signed 08/11/2018 22/01356 VOC signed 22/08/2022 | 2019 |  | Revised scheme approved 2022 with additional floor to incorporate extra bedrooms |  | TRUE | #REF!
Yes |  |  | Affordable | With Planning Permission | AD261 | Adamsdown | Longcross House, Longcross Street | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | 0 | 17/02902 Full signed 18/12/2018 | 2019 |  | Complete 2025 |  | TRUE | #REF! | -
Yes |  |  | Priv | With Planning Permission | AD268 | Adamsdown | 62 Newport Road | 0 | 17 | 17 | 17 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 17 | 0 | TRUE | 0 | 20/01608 Full 25/02/2022 | 2022 |  | Under construction | CHANGE OF USE OF OFFICES TO FORM 17 NO RESIDENTIAL FLATS AND ACCOMPANYING UPWARD EXTENSION | TRUE | #REF! | Horizon Properties
Yes |  |  | Private | With Planning Permission | AD272 | Adamsdown | Knox Court, 10 Fitzalan Place | 0 | 208 | 208 | 208 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 208 | 0 | TRUE | 0 | 24/02345 VAR 06/05/2025 | 2025 |  | Now under construction | A variation of condition application made pursuant to Section 73 of The Town and Country Planning Act 1990 to vary Conditions 2 (Approved Plans) and 10 (Ground Floor Use Class Restriction) of 22/02604/FUL, which approved: Retention of Office Space (B1/A2 Use Class) at ground floor level, 2-3 storey upward extension and change of use of Floor One - Floor Eight to create 203 units of Co-Living Accommodation (C3 Use Class) with the provision of indoor and outdoor amenity space, car/cycle parking and associated works. Permission is sought to (1) change the use of ground floor to serviced office, (2) relocate co-working space from first floor to ground floor, (3) relocate gym from second floor to ground floor and (4) increase in total units by 5 to 208.
Yes |  |  | Affordable | With Planning Permission | BU123 | Butetown | Brandon Tool Hire 151 Bute St (CCHA) | 0 | 45 | 45 | 45 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 45 | 0 | TRUE | 0 | 13/00143 outline s106 signed 16/00194 granted 20/07/2016 21/01720 granted 12/04/2022 for 45 affordable flats | 2017 |  | Under construction | Cardiff Housing site. Out to tender. Proposed start 1/02/23. Contract 18 months | TRUE | #REF! | Cardiff Council Housing
Yes |  |  | Affordable | With Planning Permission | BU132 | Butetown | Phoenix Industrial, Clarence Road Wales & West | 0 | 17 | 17 | 0 | 2026: 0; 2027: 17; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 17 | 17 | TRUE | 0 | 15/01753 Full granted 11/11/2015 | 2016 |  | Start in a few years | Site demolished. Full discharge conditions. Move to 5 year supply | TRUE | #REF! | Wales & West / Asbri Planning
Yes |  |  | Priv | With Planning Permission | BU138A | Butetown | The Wharf, 121 Schooner Way | 0 | 142 | 107 | 107 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 107 | 0 | TRUE | 0 | 16/00660 Full Committee 09/11/2016 signed 15/06/2017 | 2017 |  | Under construction |  | TRUE | #REF! | -
Yes |  |  | Affordable | With Planning Permission | BU161 | BU161 | Walters Building, Clarence Road (Cadwyn) | 0 | 35 | 35 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | TRUE | 0 | 18/02999 Full 01/04/2021 | 2022 |  |  | DEMOLITION OF THE EXISTING BUILDING AND ERECTION OF A 4/6-STOREYS RESIDENTIAL APARTMENT BLOCK COMPRISING 35 AFFORDABLE HOMES | TRUE | #REF! | Cadwyn/Asbri
Yes |  |  | Priv | With Planning Permission | BU145 | Butetown | ITEC Training Solutions, 6 Curran Road Crawshay Court | 188 | 188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | 0 | 17/01672 Full -Committee resolved to grant subject to s106 15/03/2018. Signed 07/08/2019. 19/01930 Full 10/12/2021 | 2018 |  | Complete 2025 | Revised scheme. 188 UNIT APARTMENT BUILDING WITH ANCILLARY AREAS, PARKING, PUBLIC OPEN SPACE, A1/A3 UNIT(S) AND A RESIDENTS ROOF TERRACE | TRUE | #REF! | Urban Centric (Cardiff) Ltd
Yes |  |  | Priv | With Planning Permission | BU147 | Butetown | Cardiff Bay Train Station | 0 | 10 | 10 | 0 | 2026: 10; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 10 | 10 | TRUE | 0 | 17/00224 Full 05/10/2019 | 2019 |  |  | New Site. Refurbishment complete. C3 new build link building to follow? Review next year. | TRUE | #REF! | ASBRI PLANNING
Yes |  |  | Affordable | With Planning Permission | BU160 | Butetown | The Paddle Steamer, Loudon Square | 0 | 28 | 28 | 28 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 28 | 0 | TRUE | 0 | 20/01629 Full 27/05/2021 | 2022 |  | under construction | New site PROPOSED DEMOLITION OF EXISTING STRUCTURES AND REDEVELOPMENT FOR AFFORDABLE APARTMENTS AND ASSOCIATED WORKS | TRUE | #REF! | ASBRI PLANNING
Yes |  |  | Priv | With Planning Permission | BU164 | Butetown | 68-72 James Street | 0 | 20 | 20 | 0 | 2026: 20; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 20 | 20 | TRUE | 0 | 20/02376 Full 25/02/2022 | 2023 |  | No Started |  | TRUE | #REF! | -
Yes |  |  | Priv | With Planning Permission | BU165 | Butetown | Anchor Industrial Estate | 432 | 432 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 21/02462 Full 01/07/2022 | 2023 |  | Under construction. |  | TRUE | #REF! | -
Yes |  |  | Priv | With Planning Permission | BU167A | Butetown | Central Quay Phase 2, Plot 1, Brains Brewery Site | 0 | 402 | 402 | 100 | 2026: 100; 2027: 202; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 402 | 402 | TRUE | 0 | 21/02883 Full 04/08/2022 | 2023 |  | Under construction. | Mixed use building incl. commercial at ground and residential above. 4 connected blocks height range - 13, 16, 22 & 29 storey) | TRUE | #REF! | Lichfields / Rightacres
Yes |  |  | Priv | With Planning Permission | BU167B | Butetown | Central Quay, Phase 2, Plot 2, Brains Brewery Site | 0 | 316 | 316 | 100 | 2026: 216; 2027: 0; 2028: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 316 | 316 | TRUE | 0 | 21/02884 Full 04/08/2022 | 2023 |  | Under construction. | Mixed use building incl. commercial at ground and residential above. 4 blocks height range - 8, 10, 14 & 24 storey) | TRUE | #REF! | Lichfields / Rightacres
Yes |  |  | Priv | With Planning Permission | BU170 | Butetown | Red Dragon Centre & County Hall | 0 | 890 | 890 | 0 | 0 | 0 | 100 | 150 | 150 | 150 | 180 | 160 |  |  |  | 0 | 0 | 890 | 890 | TRUE | 0 | 21/02687 Outline 27/02/2023 | 2023 |  | 2023 | Hybrid application incl. outline for up to 890 residential dwellings. | TRUE | #REF! | Cardiff Council
Yes |  |  | Priv | With Planning Permission | BU171 | Butetown | Baltic House, Mount Stuart Square | 0 | 55 | 55 | 0 | 2026: 0; 2027: 28; 2028: 27; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 55 | 55 | TRUE | 0 | 21/01037 Full s106 | 2023 |  | New Site s106 first year include | Change of use from office to residential, one storey rooftop extension (28 units) and new 6-storey residential block to rear 27 units) | TRUE | #REF! | Cardiff Council
Yes |  |  | Priv | With Planning Permission | BU168 | Butetown | St Line House, 60 Mount Stuart Square | 17 | 17 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 21/02473 Full 06/06/2022 | New site |  | Complete 2025 | Change of use to 17 apartments | TRUE | #REF!
Yes |  |  | Priv | With Planning Permission | BU173 | Butetown | 1 East Bay Close | 0 | 353 | 353 | 0 | 2026: 0; 2027: 0; 2028: 353; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 353 | 353 | TRUE | 0 | 22/01404 Full 20/06/2023 | New site |  |  | Development of 353 dwellings within 9-15 storey H-shaped building. 8 x 1 bed 1 person 167 x 1 bed 2 person 143 x 2 bed 3 person 35 x 2 bed 4 person | TRUE | #REF! | Turley
Yes |  |  | Priv | With Planning Permission | BU176 | Butetown | Suffolk House, Trade Street | 0 | 245 | 245 | 0 | 2026: 0; 2027: 100; 2028: 145; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 245 | 245 | TRUE | 0 | 22/00415 Full 27/11/2023 | New site |  |  | Demolition existing buildings, redevelopment to apartments (C3) | TRUE | #REF! | Turley
Yes |  |  | Private | With Planning Permission | BU179 | Butetown | Scott Harbour Pierhead Street | 0 | 101 | 101 |  | 2026: 51; 2027: 50 | 101 | 101 |  |  | 23/01103 Full 26/07/2024 | 2025
Yes |  |  | Priv | With Planning Permission | CN137E | Canton | Former Arjo Wiggins Paper Mill Site, Paper Mill Road | 32 | 137 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 19/03206 RM |  |  | Complete 2025 |  | TRUE | #REF! | -
Yes |  |  | Affordable | With Planning Permission | CN137F | Canton | Former Arjo Wiggins Paper Mill Site, Paper Mill Road | 8 | 77 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 19/02328 RM |  |  | Complete 2025 |  | TRUE | #REF! | -
Yes |  |  | Affordable | With Planning Permission | CN137G | Canton | Former Arjo Wiggins Paper Mill Site, Paper Mill Road | 0 | 48 | 48 | 0 | 2026: 48; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 48 | 48 | TRUE | 0 | 19/03277 MJR |  |  | New site | Accommodation for elderly persons | TRUE | #REF! | -
Yes |  |  | Priv | With Planning Permission | CN183 | Canton | Duke of Clarence Hotel, 48 Clive Road | 17 | 17 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 16/01107 Full 12/09/2017 Variation of conditions to allow additional 3 years 27/01/2021 21/02968 Full 12/01/2023. Affordable flats. | 2018 |  | Complete 2025 |  | TRUE | #REF! | Willis Construction
Yes |  |  | Affordable | With Planning Permission | CN194 | Canton | 637 Cowbridge Road East | 0 | 23 | 23 | 0 | 2026: 23; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 23 | 23 | TRUE | 0 | 19/00016 Full 26/11/2019 | 2021 |  |  | DEMOLITION OF EXISTING CAR SHOWROOM BUILDING, RELOCATION OF EXISTING ACCESSES, ERECTION OF FOUR/FIVE STOREY BUILDING TO COMPRISE 23 NO. ONE AND TWO BEDROOM AFFORDABLE HOUSING APARTMENTS AT 1ST, 2ND, 3RD AND 4TH FLOOR | TRUE | #REF! | Pegasus Developments / RPS
Yes |  |  | Affordable | With Planning Permission | CN196 | Canton | Land at Sanatorium Road (United Welsh Housing Association and Ty Mill Developments Ltd) | 0 | 69 | 69 | 0 | 2026: 20; 2027: 24; 2028: 25; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 69 | 69 | TRUE | 0 | 21/00745 Full 07/09/2021 | 2022 |  | Full consent. Propose including units in the 5 year period | NEW SITE: DEMOLITION OF THE EXISTING BUILDINGS AND ERECTION OF A NEW AFFORDABLE HOUSING DEVELOPMENT COMPRISING NEW APARTMENTS AND TOWN HOUSES | TRUE | #REF! | Turley
Yes |  |  | Affordable | With Planning Permission | CN145 | Canton | 635 Cowbridge Road East, Royal Mail Cardiff West | 0 | 20 | 20 | 0 | 2026: 0; 2027: 20; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 20 | 20 | TRUE | 0 | 07/02384 - Out S106 21/00916 Full 08/07/2022 | New site 2024 |  | New application for 20 units. Former s106 site. Has not appeared in 5 year supply. | New application for 20 units | TRUE | #REF! | RPS / Taff HA
Yes |  |  | Affordable | With Planning Permission | CN198 | Canton | Former Lionite Mele, Sanatorium Road | 0 | 35 | 35 | 0 | 2026: 8; 2027: 11; 2028: 16; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 35 | 35 | TRUE | 0 | 21/02861 Full 12/09/2022 | 2023 |  | Full consent. Discharge of conditions ongoing. Include in 5 year forecast | Demolition of existing buildings and erection of new affordable residential comprising apartments and town houses | TRUE | #REF! | Turley on behalf UWHA / Harmoni Homes
Yes |  |  | Priv | With Planning Permission | CU98A | Careau | Land South of Narbeth Road | 0 | 58 | 58 | 58 | 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 58 | 0 | TRUE | 0 | 23/00050 Full 12/11/2023 | New site 2024 |  | Under construction | Development 83 dwellings | TRUE | #REF! | Wates / Cardiff Council
Yes |  |  | Affordable | With Planning Permission | CU98B | Careau | Land South of Narbeth Road | 0 | 25 | 25 | 25 | 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 25 | 0 | TRUE | 0 | 23/00050 Full 12/11/2023 | New site 2024 |  | Under construction | Development 83 dwellings | TRUE | #REF! | Wates / Cardiff Council
Yes |  |  | Affordable | With Planning Permission | CU99 | Careau | Church of St Timothy, Heol Pennar | 0 | 15 | 15 | 15 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 15 | 0 | TRUE | 0 | 22/02825 Full 04/01/2024 | New site 2024 |  | Under construction | Demolish existing church and construction of residential development (apartments) | TRUE | #REF! | Cadwyn HA
Yes |  |  | Priv | s106 | CS278 | Cathays | 121-123 Queen Street and 40 Windsor Place | 0 | 33 | 33 | 0 | 2026: 0; 2027: 20; 2028: 13; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 33 | 33 | TRUE | 0 | 20/01346 Full. Committee 16 Dec 2020 resolved to grant subject to S.106 (first year keep in study). New application 21/01572 approved subject to s106. (additional 12 units) Conversion of the existing upper floors of the building and the addition of two new floors of residential accommodation with a roof terrace above. The ground floor retail unit will not be altered. | 2021 revised scheme 2022 |  | Retain in study as new scheme | New app. s106 first year keep in 5 year supply. CONVERSION OF UPPER FLOORS AND TWO FLOOR EXTENSION TO PROVIDE RESIDENTIAL APARTMENTS. A total of 33 new apartments will be created, arranged as follows: • First Floor: 5 one-bed studio apartments and 2 two-bed apartments; • Second Floor: 5 one-bed studio apartments and 2 two-bed apartments; • Third Floor: 5 one-bed studio apartments and 2 two-bed apartments; • Fourth Floor: 4 one-bed studio apartments and 2 two-bed apartments; • Fifth Floor: 5 one-bed studio apartments and 1 two-bed apartment. | TRUE | #REF! | Savills
Yes |  |  | Priv | With Planning Permission | CS280 | Cathays | 14 High Street | 0 | 12 | 12 | 0 | 2026: 0; 2027: 0; 2028: 12; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 12 | 12 | TRUE | 0 | 20/00750 Full 28/10/2021 | 2021 |  | Discharge of conditions nearing completion | MIXED USE DEVELOPMENT COMPRISING OF 12NO. RESIDENTIAL FLATS AND RETAIL UNIT WITH INTERNAL ALTERATIONS AND MINOR EXTERNAL ALTERATIONS TO A GRADE II LISTED BUILDING | TRUE | #REF! | Lichfields
Yes |  |  | Priv | With Planning Permission | CS284 | Cathays | 1-6 Guilford Crescent | 0 | 272 | 272 | 272 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 272 | 0 | TRUE | 0 | 21/01682 Full 12/11/2021 | 2023 |  | Under construction | Proposed mixed-use development including 272 residential apartments. | TRUE | #REF! | Lichfields
Yes |  |  | Priv | With Planning Permission | CS287 | Cathays | 117-118 St Mary Street | 0 | 12 | 12 | 0 | 2026: 0; 2027: 6; 2028: 6; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 12 | 12 | TRUE | 0 | 21/02808 Full 28/04/2022 | 2023 |  | Full consent. Discharge of conditions ongoing. Propose wholly in 5 year supply. | Change of use, internal reconfiguration, first and second floor extension and single storey rooftop extension to provide 12 flats | TRUE | #REF! | Kew Planning
Yes |  |  | Priv | With Planning Permission | CS289 | Cathays | Central Square Plots 4 & 5 | 0 | 332 | 332 | 0 | 2026: 166; 2027: 166; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 332 | 332 | TRUE | 0 | 21/02984 Full | 2023 |  | Not Started | Mixed use building providing commercial at ground floor and residential above (332 apartments) | TRUE | #REF! | Rightacres / Lichfields
Yes |  |  | Priv | With Planning Permission | CS293 | Cathays | Howells 14-18 St Mary Street | 0 | 61 | 61 | 0 | 2026: 0; 2027: 61; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 61 | 61 | TRUE | 0 | 23/02286 Full 21/12/2023 | New site 2024 |  |  | Mixed use building providing commercial at ground floor and residential above (332 apartments) | TRUE | #REF! | Rightacres / Lichfields
Yes |  |  | Priv | With Planning Permission | CS294 | Cathays | r/o 33-34 Park Place | 0 | 10 | 10 | 0 | 2026: 0; 2027: 10; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 10 | 10 | TRUE | 0 | 22/00990 Full 12/03/2024 | New site 2024 |  |  |  | TRUE | #REF!
Yes |  |  | Priv | With Planning Permission | CS297 | Cathays | 47-48 St Mary Street | 0 | 10 | 10 |  | 2026: 10 | 10 | 10 | TRUE | 0 | 21/01798 Full 21/01798 | New Site 2025 |  |  | REFURBISHMENT/EXTENSION TO EXISTING COMMERCIAL PREMISE AND CONVERSION OF OFFICE SPACE (CLASS B1) TO CREATE 10 RESIDENTIAL APARTMENTS (CLASS C3) WITH ASSOCIATED ENGINEERING WORKS
Yes |  |  | Priv | With Planning Permission | CS298 | Cathays | 16-17 High Street | 0 | 15 | 15 |  | 2026: 15 | 15 |  | TRUE |  | 23/02435 Full | New Site 2025 |  |  | Change of Use of vacant upper office floors to provide 15 apartments with roof garden. (Approved 23 July 2024- 23/02435/FUL):- Variation of Conditions 2 (Approved Plans and Documents) and omission of Condition 6 (Replacement Rooftop Rail/ Balustrade) of 23/02435/FUL to amend the approved scheme as follows: 1) Relocate the permitted cycle storage; 2) Approved green roof specification to be replaced with sedum roof; 3) Other minor reconfigurations; 4) Omission of Condition 6 as the proposed alterations will result in no persons occupying the rooftop and therefore the requirement to submit details of a replacement perimeter handrail and glass balustrade is no longer necessary.
Yes |  |  | Affordable | With Planning Permission | CS300 | Cathays | Medallion House, Crwys Road | 0 | 67 | 67 |  | 2026: 37; 2027: 30 | 67 |  | TRUE |  | 23/01914 Legal Agreement | New Site 2025 |  |  | Partial change of use of the ground floor from A1 retail to D1 community centre and A1 retail, demolition of the existing first and second floor and the construction of 64no. affordable flats on 4 new upper floors and 3no. 2-bed flats in existing car park and associated works
Yes |  |  | Priv | With Planning Permission | CY174 | Cyncoed | 17-41 Clearwater Way | 15 | 15 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 20/00153 Full Committee 27/01/2021 resolved to grant subject to s106. First year keep in study. 22/01476 VoC 8/9/2022 | 2021 |  | Complete 2025 | ERECTION OF TWO NEW FLOORS ABOVE EXISTING UNITS TO CREATE 15 ADDITIONAL APARTMENTS. | TRUE | #REF! | -
Yes |  |  | Priv | With Planning Permission | EL95 | Ely | 84-86 Sevenoaks Road | 0 | 10 | 10 | 10 | 2026: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 10 | 0 | TRUE | 0 | 16/01839 Outline resolved to grant subject to s106 09/11/2016 21/02519 RM 25/06/2021 | 2017 | Previously moved to Cat 3 to lack of progress. 2021 > RM app and 2022 > Discharge of conditions - propose moving back into land supply | Under construction |  | TRUE | #REF! | -
Yes |  |  | Priv | With Planning Permission | EL106 | Ely | Former Michaelstone College, Drope Road | 0 | 234 | 234 |  | 2026: 50; 2027: 100; 2028: 40; 2029: 44 | 234 | 234 | TRUE | 0 | 24/01264/HYB 14/11/2025 | 2025 |  |  | Full Planning Permission for the redevelopment of the Former Michaelston College Site for the Construction of a Well-Being Village Incorporating Community Living Units and Associated Communal Areas/Care Facilities (Class C2) with Community Hub (Class D1) to include cafe (Class A3), GP Surgery (Class D1), Community Hall/Meeting Space (Class D1); Residential Development (Class C3); Public Open Space; Landscaping & Green Infrastructure; Drainage; Highways; Parking, and All Associated Works;
Yes |  |  | Affordable | With Planning Permission | FA115 | Fairwater | Christchurch United, Pwellmelin Road | 0 | 19 | 19 | 19 | [13 empty] | 19 | 0 | TRUE | 0 | 22/02778 04/01/2024 | 2025 |  | Under construction | Proposed demolition of existing church, construction of residential development and associated works
Yes |  |  | Priv | With Planning Permission | GR158 | Grangetown | Cardiff Pointe (Figurehead Homes) | 0 | 561 | 462 | 0 | 62 | 75 | 50 | 50 | 75 | 75 | 75 |  |  |  |  | 0 | 0 | 462 | 462 | TRUE | 0 | Local Plan alloc. 05/615 June 2005 997 units; 05/1574 Oct 2006 1127 units; 07/1276 for 1,801 units (S106); 12/937 Full 5/4/13 Cardiff Council has acquired this site. New plans to follow. | 2012 |  | No progress. Retain Cat 3 |  | TRUE | #REF! | Cardiff Council
Yes |  |  | Priv | With Planning Permission | GR192 | Grangetown | Track 2000, 54B Penarth Road | 0 | 74 | 74 | 74 | 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 74 | 0 | TRUE | 0 | 18/02622 Full 29/11/2019 | 2021 |  | Application progressing (discharge of conditions and non-material design changes) NMA 23/02942/NMA | New site. ERECTION OF A RESIDENTIAL DEVELOPMENT OF 74 UNITS WITH ASSOCIATED INFRASTRUCTURE AND ENGINEERING WORKS | TRUE | #REF! | Rightacres / Lichfields
Yes |  |  | HA | With Planning Permission | GR196A | Grangetown | Land at Channel View (Cardiff Council) Phases 2-7 | 0 | 319 | 319 | 0 | 0 | 60 | 60 | 60 | 70 | 69 | [5 empty] | 0 | 0 | 319 | 319 | TRUE | 0 | 21/01666 Outline 19/10/2022 | 2022 |  | Cardiff Council site. Outline part of application (phases 2-7) | HYBRID APPLICATION MIXED-USE DEVELOPMENT OUTLINE: REDEVELOPMENT OF CHANNEL VIEW ESTATE FOR UP TO 319 RESIDENTIAL APARTMENTS AND HOUSES, FULL PERMISSION: FIRST PHASE COMPRISING NEW TOWER BLOCKS (8-13 STOREYS) PROVIDING 81 OLDER-PERSONS (OVER 55S), COMMUNITY-LIVING ACCOMMODATION UNITS, | TRUE | #REF! | Cardiff Council
Yes |  |  | HA | With Planning Permission | GR196B | Grangetown | Land at Channel View (Cardiff Council) Phase 1 | 0 | 81 | 81 | 19 | 2026: 26; 2027: 26; 2028: 10; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 81 | 62 | TRUE | 0 | 21/01666 Outline 19/10/2022 | 2022 | Cardiff Council site. Full part of application. Proposed start on site 01/09/2022. Contract period 18 Months | Under construction | HYBRID APPLICATION MIXED-USE DEVELOPMENT OUTLINE: REDEVELOPMENT OF CHANNEL VIEW ESTATE FOR UP TO 319 RESIDENTIAL APARTMENTS AND HOUSES, FULL PERMISSION: FIRST PHASE COMPRISING NEW TOWER BLOCKS (8-13 STOREYS) PROVIDING 81 OLDER-PERSONS (OVER 55S), COMMUNITY-LIVING ACCOMMODATION UNITS, | TRUE | #REF! | Cardiff Council
Yes |  |  | Priv | With Planning Permission | LD134A | Llandaff | BBC Llantrisant Road | 17 | 184 | 167 | 46 | 2026: 50; 2027: 50; 2028: 21; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 167 | 121 | TRUE | 0 | 15/00799 Outline 05/11/2015 16/01059 RM 03/11/2016 364 new dwellings | 2016 |  | Under construction | FULL DETAILS OF RESERVED MATTERS FOR REDEVELOPMENT OF THE SITE FOR RESIDENTIAL DEVELOPMENT (364 NO. DWELLINGS) WITH NEW PUBLIC OPEN SPACE, LANDSCAPING AND HIGHWAYS INFRASTRUCTURE (INCLUDING ACCESSES AND PATHS), REQUIRING: THE DEMOLITION OF ALL EXISTING STRUCTURES, SITE CLEARANCE, SITE PREPARATION, THE INSTALLATION OF NEW SERVICES AND INFRASTRUCTURE AND OTHER ASSOCIATED WORKS AND ACTIVITIES | TRUE | #REF! | Taylor Wimpey UK Limited / Savills
Yes |  |  | Affordable | With Planning Permission | LD134B | Llandaff | BBC Llantrisant Road | 0 | 95 | 95 | 95 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 95 | 0 | TRUE | 0 | 15/00799 Outline 05/11/2015 16/01059 RM 03/11/2016 364 new dwellings in total | 2016 |  | Under construction | FULL DETAILS OF RESERVED MATTERS FOR REDEVELOPMENT OF THE SITE FOR RESIDENTIAL DEVELOPMENT (364 NO. DWELLINGS) WITH NEW PUBLIC OPEN SPACE, LANDSCAPING AND HIGHWAYS INFRASTRUCTURE (INCLUDING ACCESSES AND PATHS), REQUIRING: THE DEMOLITION OF ALL EXISTING STRUCTURES, SITE CLEARANCE, SITE PREPARATION, THE INSTALLATION OF NEW SERVICES AND INFRASTRUCTURE AND OTHER ASSOCIATED WORKS AND ACTIVITIES | TRUE | #REF! | Taylor Wimpey UK Limited / Savills
Yes |  |  | Private | With Planning Permission | LD134C | Llandaff | BBC Llantrisant Road | 3 | 85 | 49 |  | 2026: 39; 2027: 10 | 49 | 49 | TRUE | 0 | 19/03240 08/06/2021 | 2022 |  | Under construction | RESERVED MATTERS PURSUANT TO 15/00799/MJR IN RESPECT OF APPEARANCE, LANDSCAPING, LAYOUT AND SCALE
Yes |  |  | Priv | With Planning Permission | LD138 | Llandaff | 58 Pwllmelin Road | 0 | 23 | 23 | 0 | 2026: 5; 2027: 6; 2028: 12; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 23 | 23 | TRUE | 0 | 20/01882 Full signed August 2023 | 2023 |  |  | Demolish existing dwelling and replacement with 23 apartments within 4 blocks | TRUE | #REF! | Lichfields
Yes |  |  | Priv | With Planning Permission | LD139 | Llandaff | Land at Former Waste Centre. Waun Gron Park | 0 | 44 | 44 | 0 | 2026: 22; 2027: 22; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 44 | 44 | TRUE | 0 | 21/01359 Full 31/05/22 | 2023 |  | Not Started | Mixed use comprising 44 1 & 2 bed apartments | TRUE | #REF! | Cardiff Council Housing
Yes |  |  | Priv | With Planning Permission | LR48A | Llanrumney | Former Llanrumney High School, Ball Road | 28 | 70 | 42 | 34 | 2026: 8; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 42 | 8 | TRUE | 0 | 18/02594 Full 29/08/2019 | 2019 |  | Cardiff Council Housing Development. Under construction. | Cardiff Living Phase 2. | TRUE | #REF! | Cardiff Council Housing
Yes |  |  | Affordable | With Planning Permission | LR48B | Llanrumney | Former Llanrumney High School, Ball Road (Affordable) | 0 | 28 | 28 | 24 | 2026: 4; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 28 | 4 | TRUE | 0 | 18/02594 Full 29/08/2019 | 2019 |  | Cardiff Council Housing Development. Under construction. | Cardiff Living Phase 2. | TRUE | #REF! | Cardiff Council Housing
Yes |  |  | Affordable | With Planning Permission | LS208 | Llanishen | Iorwerth Jones, Home for the Elderly (Hale) | 20 | 20 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 20/02068 Full 28/05/2021 | 2022 |  | Site Complete 2025 |  | TRUE | #REF! | Cardiff Council Housing
Yes |  |  | Private | With Planning Permission | LS215 | Llanishen | 30-36 Fishguard Road | 0 | 20 | 20 |  | 2026: 10; 2027: 10 | 20 | 20 | TRUE | 0 | 21/02863 29/08/2025 | 2025 |  |  | PROPOSED DEMOLITION OF EXISTING GARAGES AND ERECTION OF NEW ATTACHED DEVELOPMENT TO FORM FLATS
Yes |  |  | Priv | With Planning Permission | LV06 | Lisvane & Thornhill | Land south of Lisvane Road | 0 | 40 | 5 | 0 | 2026: 5; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 5 | 5 | TRUE | 0 | Outline app 03/1930 approved 16/10/03 - still dependant on Julian Hodge? (Deceased) 06/1442 - Renewal of outline. 06/01442 signed 13/08/2008. ARM submitted July 11 11/01300 40 units, 27/3/13. 15/00036 Certificate of Lawfulness 06/03/2015 | Wholly included 2012. In 2010 20 units in 5 ys, 20 in 3(i). |  | Under construction |  | TRUE | #REF! | Edenstone Homes
Yes |  |  | Priv | With Planning Permission | LV76 | Lisvane & Thornhill | Land N of Lisvane Rd (Balmoral Close) | 7 | 23 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 08/01929 extend period for ARM to 12-08-11 (earlier app 06/01443). 11/01301 ARM 27/03/13. 15/00462 Certificate of Lawfulness 09/04/2015 | 2011 |  | Complete 2025 |  | TRUE | #REF! | Edenstone Homes
Yes |  |  | Priv | With Planning Permission | PL228 | Plasnewydd | 5-7 Oakfield Street | 0 | 10 | 10 | 0 | 2026: 0; 2027: 10; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 10 | 10 | TRUE | 0 | 15/00306 Full 01/08/2017 23/00040 Full signed 19 August 2024 | 2016 |  | New application received (approved after base date) will re-appear in landbank next year for 10 units) | Demolition and construction of apartments | TRUE | #REF! | -
Yes |  |  | Priv | With Planning Permission | PL270 | Plasnewydd | 160-166 Strathnairn Street | 0 | 10 | 10 | 0 | 2026: 0; 2027: 10; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 10 | 10 | TRUE | 0 | 20/00361 Full 23/07/2020 | 2021 |  | No Started | DEMOLITION OF EXISTING BUILDINGS AND CONSTRUCTION OF 12NO. SELF CONTAINED APARTMENTS | TRUE | #REF! | C2J Architects & Town Planners
Yes |  |  | Affordable | With Planning Permission | PL287 | Plasnewydd | Albany Road Baptish Church | 0 | 12 | 12 | 12 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 12 | 0 | TRUE | 0 | 21/02538 Full 10/03/2023 | 2023 |  | Under construction | 12 Affordable flats | TRUE | #REF! | -
Yes |  |  | Priv | With Planning Permission | PL288 | Plasnewydd | 69-71 Richmond Road | 0 | 12 | 12 | 12 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 12 | 0 | TRUE | 0 | 21/00243 Full 20/04/2023 | New site 2024 |  | Under construction | Hotel to flats | TRUE | #REF! | -
Yes |  |  | Priv | With Planning Permission | PL291 | Plasnewydd | Land at Bedford Place | 0 | 18 | 18 | 0 | 2026: 0; 2027: 18; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 18 | 18 | TRUE | 0 | 23/00145 Full 17/10/2023 | New site 2024 |  |  | 18 flats, YMCA car park | TRUE | #REF! | ASBRI PLANNING
Yes |  |  | Affordable | With Planning Permission | PL293 | Plasnewydd | Former Youth Hostel | 0 | 23 | 23 | 0 | 2026: 0; 2027: 23; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 23 | 23 | TRUE | 0 | 22/00820 Full 14/03/2024 | New site 2024 |  |  | 5 storey building to accommodate 23 affordable flats | TRUE | #REF! | ASBRI PLANNING
Yes |  |  | Private | With Planning Permission | PL294 | Plasnewydd | The Roath Park, 170 City Road | 0 | 20 | 20 |  | 2026: 0; 2027: 10; 2028: 10 | 20 | 20 | TRUE | 0 | 23/00492 Full | New Site 2025 |  |  | Proposed retention of the principal facades of the former public house, with an upward extension to the roof; demolition of secondary protrusion on Kincraig Street frontage and its replacement with a three -storey structure. Proposed residential use as 20 flats with commercial uses on part of the ground floor and basement.
Yes |  |  | Priv | With Planning Permission | PW26 | Pentwyn | 56 Wern Goch West | 0 | 18 | 18 | 0 | 2026: 0; 2027: 18; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 18 | 18 | TRUE | 0 | 18/01028 Full 08/10/2020 23/00632 Full 12/01/2024 | 2019 |  | New conversion scheme increased no. units 11 to 18 | Conversion of existing buildings and additional floors to create 18 self contained apartments | TRUE | #REF! | Berriman Developments Ltd
Yes |  |  | Affordable | With Planning Permission | PW29 | Pentwyn | Former Police Station, Maelfa | 0 | 41 | 41 | 41 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 41 | 0 | TRUE | 0 | 19/03219 Full 30/04/2020 | 2021 |  | Under construction | DEMOLITION OF EXISTING GARAGES AND DEVELOPMENT OF 41NO. INDEPENDENT LIVING CARE-READY FLATS AND ASSOCIATED WORKS | TRUE | #REF! | Cardiff Council Housing
Yes |  |  | Affordable | With Planning Permission | PW33 | Pentwyn | The New Penn, 204a Brynfedw | 0 | 11 | 11 | 0 | 2026: 0; 2027: 5; 2028: 6; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 11 | 11 | TRUE | 0 | 23/02475 Full 14/03/2023 resolved to grant/s106 signed 15/04/2024 | New site 2024 |  | Cardiff Council scheme | Demolition of former public house and redevelopment of site to affordable dwellings | TRUE | #REF! | Cardiff Council Housing
Yes |  |  | Affordable | With Planning Permission | PW34 | Pentwyn | Land West of St Teilos School | 0 | 53 | 53 |  | 2027: 20; 2028: 33 | 53 | 53 | TRUE | 0 | 24/01603 11/02/2025 | New Site 2025 |  | Cardiff Council Scheme | Proposed development of 53 council homes, nine supported living apartments, re-alignment of footpath, sustainable drainage proposals, landscape planting including an ecotone, and associated works.
Yes |  |  | Priv | With Planning Permission | RA78 | Radyr & Morganstown | 45-47 Drysgol Road | 0 | 19 | 19 | 0 | 2026: 10; 2027: 9; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 19 | 19 | TRUE | 0 | 18/01820 Full 21/03/2019 | 2021 |  |  | PROPOSED DEMOLITION OF EXISTING DWELLINGS & OUTBUILDINGS. CONSTRUCTION OF TWO 3 STOREY BLOCKS, EACH OF 9 SELF CONTAINED APARTMENTS / DETACHED 4 BED DWELLING WITH NEW ACCESS ONTO DRYSGOL ROAD | TRUE | #REF! | C2JARCHITECTS & TOWN PLANNERS
Yes |  |  | Priv | With Planning Permission | RO129 | Penylan | Colchester Motor Company, Colchester Avenue | 50 | 50 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 16/02882 Full 12/04/2017 20/01255 Full 11/03/2021 | 2018 |  | Site Complete 2025 |  | TRUE | #REF! | -
Yes |  |  | Priv | With Planning Permission | RU117A | Rumney | Eastern High School, Newport Road | 13 | 149 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 18/02519 Full 23/01/2019 | 2021 |  | Site Complete 2025 | Cardiff Living Phase 2 FULL PLANNING APPLICATION FOR THE PROPOSED RESIDENTIAL DEVELOPMENT OF 214 HOMES COMPRISING 149 GENERAL MARKET HOMES AND 65 AFFORDABLE HOMES (WHICH INCLUDES A 44 BED OLDER PERSONS' INDEPENDENT LIVING ACCOMMODATION BLOCK) | TRUE | #REF! | -
Yes |  |  | Affordable | With Planning Permission | RU117B | Rumney | Eastern High School, Newport Road | 8 | 65 | 0 | 0 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 0 | 0 | TRUE | 0 | 18/02519 Full 23/01/2019 | 2021 |  | Site Complete 2025 | Cardiff Living Phase 2 FULL PLANNING APPLICATION FOR THE PROPOSED RESIDENTIAL DEVELOPMENT OF 214 HOMES COMPRISING 149 GENERAL MARKET HOMES AND 65 AFFORDABLE HOMES (WHICH INCLUDES A 44 BED OLDER PERSONS' INDEPENDENT LIVING ACCOMMODATION BLOCK) | TRUE | #REF! | -
Yes |  |  | Priv | With Planning Permission | RU107 | Rumney | 599 Newport Road | 0 | 32 | 32 | 0 | 2026: 0; 2027: 15; 2028: 17; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 32 | 32 | TRUE | 0 | 15/00362 Full Committee 15/06/2016 resolved to grant subject to s106. Signed 15/09/2017. 20/02200 granted 21/01/2021 18/00787 Non Material Amendment to conditions 17/05/2018 | 2017 |  |  | AMENDMENTS AS FOLLOWS: 1. BLOCKS A & B - LOBBY ENTRANCES ENLARGED TO ACCOMMODATE M&E; 2. BLOCKS A & B - INTERNAL FLOOR HEIGHTS INCREASED WITH OVERALL ROOF HEIGHTS INCREASED TO ACCOMMODATE M&E; 3. BLOCKS A & B - PLANT ROOM AND STAIRCASE ENCLOSURE ADDED TO THE FLAT ROOF; 4. BLOCKS A & B - PHOTOVOLTAIC PANELS ADDED TO FLAT ROOF; 5. SPRINKLER TANK ADDED TO NORTHERN END OF SITE REPLACING TWO VISITOR PARKING SPACES; 6. BLOCK A RE-POSITIONED TO FACILITATE THE PILING DESIGN; 7. ACCESS CREATED FOR WESTERN POWER SUB STATION REQUIRED BY WESTERN POWER - PREVIOUSLY APPROVED UNDER 15/00362/MJR | TRUE | #REF! | DLP / Spiteri
Yes |  |  | Priv | With Planning Permission | RU118 | Rumney | 782-786 Newport Road | 0 | 27 | 27 | 0 | 2026: 0; 2027: 0; 2028: 27; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 27 | 27 | TRUE | 0 | 19/01533 Full 16/03/2021 | 2022 |  |  | DEMOLITION OF EXISTING BUILDINGS, MIXED USE DEVELOPMENT COMPRISING RESIDENTIAL (1 Block 27 x 1 bed flats) & RETAIL. | TRUE | #REF! | M2M Architects Ltd
Yes |  |  | Affordable | With Planning Permission | RV253 | Riverside | Canton Community Hall, Leckwith Road | 0 | 41 | 41 | 41 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 41 | 0 | TRUE | 0 | 21/01806 Full 07/02/2022 | 2022 |  | Under construction | DEMOLITION OF EXISTING CANTON COMMUNITY CENTRE, CAR PARK AND MUGA; PROPOSED DEVELOPMENT OF COMMUNITY LIVING SCHEME COMPRISING OF 41 FLATS, COMMUNITY HALL, MULTI-USE GAMES AREAS. Council housing site. Contract 18 months | TRUE | #REF! | Cardiff Council Housing Development Team
Yes |  |  | Affordable | With Planning Permission | RV260 | Riverside | 51-65 Cowbridge Road East | 0 | 81 | 81 | 0 | 2026: 0; 2027: 40; 2028: 41; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 81 | 81 | TRUE | 0 | 22/02901 Full 03/08/2023 | New site 2024 |  |  | Demolish existing structures and the replacement with mixed use with residential on upper floors (2 to 7 storeys variable height) | TRUE | #REF! | Wales and West HA
Yes |  |  | Priv | With Planning Permission | SP150 | Splott | Moorland Road Day Centre, Moorland Road | 0 | 13 | 13 | 0 | 2026: 0; 2027: 6; 2028: 7; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 13 | 13 | TRUE | 0 | 22/01718 Full 10/03/2023 | 2023 |  |  | Cardiff Council Housing Development Site | TRUE | #REF! | Cardiff Council Housing Development Team
Yes |  |  | Priv | With Planning Permission | TR157A | Trowbridge | St Mellons Community Centre, Crickhowell Road. | 0 | 60 | 60 | 60 | 2026: 0; 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 60 | 0 | TRUE | 0 | 16/01680 Outline committee 28/09/2016 resolved to grant subject to s106. Signed 12/07/2017. 19/03320 Full 29/04/2020 | 2017 |  | Under construction | Council housing scheme. Demolition complete | TRUE | #REF! | Cardiff Council Housing
Yes |  |  | Priv | With Planning Permission | TR160A | Trowbridge | Land off Willowbrook Drive | 0 | 39 | 39 | 39 | 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 39 | 0 | TRUE | 0 | 16/01670 Outline 02/02/2018 21/00770 RM 20/08/2021 | 2018 |  | Under construction | RESERVED MATTERS APPROVAL (LAYOUT, SCALE, APPEARANCE, ACCESS AND LANDSCAPING) IN RESPECT OF 70 HOMES AND ASSOCIATED WORKS AND INFRASTRUCTURE PURSUANT TO OUTLINE PLANNING APPROVAL 19/03260/MJR | TRUE | #REF! | Cardiff Council Housing
Yes |  |  | Affordable | With Planning Permission | TR160B | Trowbridge | Land off Willowbrook Drive (Affordable) | 0 | 31 | 21 | 21 | 2027: 0; 2028: 0; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 21 | 0 | TRUE | 0 | 16/01670 Outline 02/02/2018 21/00770 RM 20/08/2021 | 2018 |  | Under construction | RESERVED MATTERS APPROVAL (LAYOUT, SCALE, APPEARANCE, ACCESS AND LANDSCAPING) IN RESPECT OF 70 HOMES AND ASSOCIATED WORKS AND INFRASTRUCTURE PURSUANT TO OUTLINE PLANNING APPROVAL 19/03260/MJR | TRUE | #REF! | Cardiff Council Housing
[8 empty] | 1338 | 23653 | 20697 | 1807 | 1738 | 2219 | 1925 | 1522 | 1836 | 1933 | 1830 | 1715 | 1496 | 1174 | 952 | 0 | 0 | 20147 | 18476 |  | 550
THE SITES BELOW ARE SUBJECT TO S106 AGREEMENTS AND ARE NOT INCLUDED IN THE 5-YEAR LAND SUPPLY CALCULATION.
PRIVATE - SITES WITH PLANNING PERMISSION SUBJECT TO S106
Yes |  |  | Priv | S106 | GR156A | Grangetown | Land at Wholesale Fruit Centre | 0 | 215 | 215 | 0 | 2026: 50; 2027: 50; 2028: 50; 2029: 50; Beyond 2036 Cat 3: 15; Beyond 2036 Cat 4: 0 | 200 | 215 |  |  | 10/01432 (Full) subject to s106 | s106 site. Has not appeared in 5 year supply. |  |  | No change proposed. | TRUE | #REF! | -
[8 empty] | 0 | 215 | 215 | 0 | 2026: 50; 2027: 50; 2028: 50; 2029: 50; Beyond 2036 Cat 3: 15; Beyond 2036 Cat 4: 0 | 200 | 215 | [7 empty] | TRUE | #REF!
|  |  | AFFORDABLE - SITES WITH PLANNING PERMISSION SUBJECT TO S106 | [30 empty] | TRUE | #REF!
Yes |  |  | Affordable | S106 | GR156B | Grangetown | Land at Wholesale Fruit Centre | 0 | 35 | 35 | 0 | 2026: 0; 2027: 0; 2028: 35; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 35 | 35 |  |  | 10/01432 (Full) subject to s106 | s106 site. Has not appeared in 5 year supply. |  |  | No change proposed. |  |  | -
[8 empty] | 0 | 35 | 35 | 0 | 2026: 0; 2027: 0; 2028: 35; 2029: 0; Beyond 2036 Cat 3: 0; Beyond 2036 Cat 4: 0 | 35 | 35 | [7 empty] | TRUE | #REF!
|  |  | Grand Total All Sites |  |  |  | Grand Total All Sites | 1338 | 23903 | 20947 | 1807 | 2026: 1788; 2027: 2269; 2028: 2010; 2029: 1572; Beyond 2036 Cat 3: 15; Beyond 2036 Cat 4: 0 | 20382 | 18726
[8 empty] | 1338 | 47806 | 41894 | 3614 | 2026: 3576; 2027: 4538; 2028: 4020; 2029: 3144; Beyond 2036 Cat 3: 30; Beyond 2036 Cat 4: 0 | 40764 | 37452
[9 empty] | 23903 | 20947 | 1807 | 2026: 1788; 2027: 2269; 2028: 2010; 2029: 1572; Beyond 2036 Cat 3: 15; Beyond 2036 Cat 4: 0 | 20382 | 18726
[9 empty] | TRUE | TRUE | TRUE | 2026: TRUE; 2027: TRUE; 2028: TRUE; 2029: TRUE; Beyond 2036 Cat 3: TRUE; Beyond 2036 Cat 4: TRUE | TRUE | TRUE
Note on M1: Strangis, James: Sites or the phases of sites which are under construction (relating only to the area where building is in progress).
Note on Y2: Strangis, James: Sites or phases of sites where the Study Group agree that it is not financially viable to develop the site due to market conditions, but which are otherwise free from constraints. (Although Category 3 sites will not form part of the 5-year supply, their identification may assist local planning authorities, developers and landowners in finding opportunities to improve site viability and deliverability.)
Note on Z2: Strangis, James: Sites or the phases of sites where development is unlikely within 5 years by virtue of major physical constraints or other constraints as agreed by the Study Group.